## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Set Up Git Repository with main and Dev branches | MUST HAVE | - | Arsath Maideen | 3- Completed
S1 | S1 | US-002 | Create and document the ER Diagram | MUST HAVE | - | Arsath Maideen | 3- Completed
S1 | S1 | US-003 | Create Eligibility Criteria Workflow Diagram with proper workflow steps mentioned | MUST HAVE | - | Akshay Menon | 3- Completed
S1 | S1 | US-004 | Project discussion with team for workflow diagram | MUST HAVE | - | Archana | 3- Completed
S1 | S1 | US-005 | Create and document the Business Logic Workflow of the Application | MUST HAVE | US-004 | Jeevan Manoj | 3- Completed
S1 | S1 | US-006 | Give API endpoints and status codes | MUST HAVE | - | Praveena | 3- Completed
S1 | S1 | US-007 | Create API - Design Document with Module Based diagram | MUST HAVE | US-006 | Akshay Menon | 3- Completed
S1 | S1 | US-008 | Research on OCR implementation in the Eligibility Criteria Engine | COULD HAVE | US-003 | Akshay Menon | 4-Couldn't Complete
S2 | S2 | US-009 | Team Discussion, Requirement Analysis & Project Planning | MUST HAVE | - | Archana | 3- Completed
S2 | S2 | US-010 | Development of static login page with demo credentials , demo workflow of registration process in the system | MUST HAVE | US-005 | Pravenna | 3- Completed
S2 | S2 | US-011 | Development of community dashboard for users, added demo schemes, tracking subsidy application status | MUST HAVE | US-005 | Archana | 3- Completed
S2 | S2 | US-012 | Developed Officer Dashboard with well analytics layout, designed application management module. | MUST HAVE | US-005 | Sahanaa | 3- Completed
S2 | S2 | US-013 | Developed admin's login, admin's dashboard with audit logs as seperate section,ability to manipulate schemes | MUST HAVE | US-005 | Archana | 3- Completed
S2 | S2 | US-014 | Setup Spring Boot backend from Spring Initialiser, tested basic APIs, and pushed code to Git Repo. | MUST HAVE | - | Akshay Menon | 3- Completed
S2 | S2 | US-015 | Developed APIs for login, signup, delete, get-profile, update-profile. | MUST HAVE | - | Akshay Menon | 3- Completed
S2 | S2 | US-016 | Developed JWT Authentication from generation of tokens to validation with API's protected and restricted w.r.t roles | MUST HAVE | - | Akshay Menon | 3- Completed
S2 | S2 | US-017 | Developed APIs for beneficiary modules, scheme modules and audit logs. | MUST HAVE | - | Jeevan Manoj | 3- Completed
S2 | S2 | US-018 | Updated beneficiary modules and scheme modules as per discussion with backend team | MUST HAVE | - | Jeevan Manoj | 3- Completed
S2 | S2 | US-019 | Created APIs for Application management module, Updated APIs for scheme modules | MUST HAVE | US-009 | Arsath Maideen | 3- Completed
-
S3 | S3 | US-020 | Discussion with Team Members, Requirement Analysis & Project Planning | MUST HAVE | - | Frontend Team | 3- Completed
S3 | S3 | US-021 | Developed Finance Officer Dashboard with features included like create fund disbursement, initiate fund disbursement to approved applications better UI controls | MUST HAVE | US-004 | Archana | 3- Completed
S3 | S3 | US-022 | Updated File structure of frontend according to industrial approach | MUST HAVE | - | Akshay Menon | 3- Completed
S3 | S3 | US-023 | Integration of Frontend and Backend APIs of Modules 1.Auth Module , 2. Admin Module, 3. Officer Module, 4. Scheme Module as well as 5. Beneficiary Module | MUST HAVE | - | Akshay Menon | 3- Completed
S2 | S3 | US-024 | Worked on reamining M2 -- officer workflow | MUST HAVE | - | Arsath Maideen | 3- Completed
S3 | S3 | US-025 | Started working on M3-modules | MUST HAVE | - | Arsath Maideen | 2- In Progress
S3 | S3 | US-026 | Worked on Staged Disbursement & Milestone Scheduling | MUST HAVE | - | Jeevan Manoj | 3- Completed
S3 | S3 | US-027 | Worked on Compliance Tracking & Reminder Automation | MUST HAVE | - | Jeevan Manoj | 3- Completed
S3 | S2 | US-028 | Developed Stage By stage Approval for Beneficiary Application Flow as Backend APIs | MUST HAVE | - | Akshay Menon | 3- Completed
S3 | S3 | US-029 | Given Idea for the analytics dashboard for each officer as per their requirements based on existing database entities | MUST HAVE | - | Jeevan Manoj | 2- In Progress
S3 | S3 | US-030 | Developed Analytics Dashboard for each officer UI which has data visualisation tools like pie chart , bar charts and other form of data visuals | MUST HAVE | - | Akshay Menon | 3- Completed
S3 | S3 | US-031 | Developed code for backend by sending required DTO's to frontend for data visualisation in Analytics Dashboard | MUST HAVE | - | Akshay Menon | 3- Completed
S1 | S4 | US-032 | Verification and testing for beneficiary login and signup and data saved in the Database | MUST HAVE | - | Arsath Maideen | 3- Completed
S2 | S4 | US-033 | Testing done by handling various test cases provided by the mentor for application submission module done by beneficiary | MUST HAVE | - | Arsath Maideen | 3- Completed
S2 | S4 | US-034 | Testing for officer registration as well as approving request by admin leading to registration successfull of officers to login done successfully | MUST HAVE | - | Arsath Maideen | 3- Completed
S3 | S4 | US-035 | Testing for Admin allocating the applications to 4 different officers done successfully. Along with stage based approval done by each officer leading to clean flow of the application documents reaching successfully to the finance officer ready for the disbursement. | MUST HAVE | - | Arsath Maideen | 3- Completed
S3 | S4 | US-036 | Testing for Stage by Stage Disbursement funds to the beneficary done successfully | MUST HAVE | - | Arsath Maideen | 3- Completed
S3 | S4 | US-037 | Modified the frontend UI of Admins Dashboard with better navigation to each pages, developed a system to allocate a applications to each officer wrt to each stage by having a control number of applications that a each officer needs to be allocated setted by admins | MUST HAVE | - | Akshay Menon | 3- Completed
S4 | S4 | US-038 | Modified the backend APIs correcting the flow of the application documents and identified the bugs corrected them seamlessly | MUST HAVE | - | Akshay Menon | 3- Completed
S4 | S4 | US-039 | Updated frontend Officer dashboard by adding the field inspection report to field officer which needs to be submitted, regional officer approves the field inspection report, district officer authenticates the beneficiary documents with the filled fields. | MUST HAVE | - | Akshay Menon | 3- Completed
S4 | S4 | US-040 | Updated frontend as well as the backend of the beneficary module management eliminating the bugs | MUST HAVE | - | Akshay Menon | 3- Completed
S4 | S4 | US-041 | Integrated Security Based Roles, restricted APIs Roles based access,Authentication and authorization to the roles. | MUST HAVE | - | Akshay Menon | 3- Completed
Note on F1: ====== ID#AAACAAPd2c4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 710 | 212 | 104 | 37 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note: totals above sum each task's OWN Day-1..Day-14 (task-relative), not a shared calendar day across the project. Use the per-sprint TOTAL EFFORT rows below for real sprint totals.
SPRINT 1 BACKLOG
US-001 | 1 | Set Up Git Repository with main and Dev branches | 2025-06-30 | 2025-06-30 | Arsath Maideen | Coding | 3- Completed | 4 | Day 1: 4
US-002 | 2 | Create and document the ER Diagram | 2025-07-01 | 2025-07-01 | Arsath Maideen | Design | 3- Completed | 4 | Day 1: 4
US-003 | 3 | Create Eligibility Criteria Workflow Diagram with proper workflow steps mentioned | 2025-07-03 | 2025-07-04 | Akshay Menon | Design | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-004 | 4 | Project discussion with team for workflow diagram | 2025-07-05 | 2025-07-05 | Archana | Design | 3- Completed | 4 | Day 1: 4
US-005 | 5 | Create and document the Business Logic Workflow of the Application | 2025-07-07 | 2025-07-08 | Jeevan Manoj | Design | 3- Completed | 5 | Day 1: 4; Day 2: 1
US-006 | 6 | Give API endpoints and status codes | 2025-07-08 | 2025-07-08 | Praveena | Coding | 3- Completed | 4 | Day 1: 4
US-007 | 7 | Create API - Design Document with Module Based diagram | 2025-07-10 | 2025-07-11 | Akshay Menon | Design | 3- Completed | 5 | Day 1: 4; Day 2: 1
US-008 | 8 | Research on OCR implementation in the Eligibility Criteria Engine | 2025-07-12 | 2025-07-12 | Akshay Menon | Others | 4-Couldn't Complete | 4 | Day 1: 4
|  | S1 TOTAL EFFORT (HOURS) | [5 empty] | 36
SPRINT 2 BACKLOG
US-009 | 1 | Team Discussion, Requirement Analysis & Project Planning | 2025-07-14 | 2025-07-14 | Archana | Others | 3- Completed | 4 | Day 1: 4
US-010 | 2 | Development of static login page with demo credentials , demo workflow of registration process... | 2025-07-15 | 2025-07-16 | Praveena | Coding | 3- Completed | 7 | Day 1: 4; Day 2: 3
US-011 | 3 | Development of community dashboard for users, added demo schemes, tracking subsidy application... | 2025-07-16 | 2025-07-18 | Archana | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-011 | 4 | Development of community dashboard for users, added demo schemes, tracking subsidy application... | 2025-07-19 | 2025-07-21 | Archana | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-012 | 5 | Developed Officer Dashboard with well analytics layout, designed application management module.... | 2025-07-17 | 2025-07-19 | Sahanaa | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-012 | 6 | Developed Officer Dashboard with well analytics layout, designed application management module.... | 2025-07-20 | 2025-07-22 | Sahanaa | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-013 | 7 | Developed admin's login, admin's dashboard with audit logs as seperate section,ability to manip... | 2025-07-18 | 2025-07-20 | Archana | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-013 | 8 | Developed admin's login, admin's dashboard with audit logs as seperate section,ability to manip... | 2025-07-21 | 2025-07-23 | Archana | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-014 | 9 | Setup Spring Boot backend from Spring Initialiser, tested basic APIs, and pushed code to Git Re... | 2025-07-19 | 2025-07-19 | Akshay Menon | System Test | 3- Completed | 4 | Day 1: 4
US-015 | 10 | Developed APIs for login, signup, delete, get-profile, update-profile. | 2025-07-21 | 2025-07-22 | Akshay Menon | Coding | 3- Completed | 5 | Day 1: 4; Day 2: 1
US-016 | 11 | Developed JWT Authentication from generation of tokens to validation with API's protected and r... | 2025-07-22 | 2025-07-24 | Akshay Menon | Coding | 3- Completed | 8 | Day 1: 4; Day 2: 3; Day 3: 1
US-016 | 12 | Developed JWT Authentication from generation of tokens to validation with API's protected and r... | 2025-07-25 | 2025-07-27 | Akshay Menon | Coding | 3- Completed | 8 | Day 1: 4; Day 2: 3; Day 3: 1
US-017 | 13 | Developed APIs for beneficiary modules, scheme modules and audit logs. | 2025-07-23 | 2025-07-24 | Jeevan Manoj | Coding | 3- Completed | 5 | Day 1: 4; Day 2: 1
US-018 | 14 | Updated beneficiary modules and scheme modules as per discussion with backend team | 2025-07-24 | 2025-07-25 | Jeevan Manoj | Others | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-019 | 15 | Created APIs for Application management module, Updated APIs for scheme modules | 2025-07-25 | 2025-07-26 | Arsath Maideen | Coding | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-028 | 16 | Developed Stage By stage Approval for Beneficiary Application Flow as Backend APIs | 2025-07-26 | 2025-07-27 | Akshay Menon | Coding | 3- Completed | 6 | Day 1: 4; Day 2: 2
|  | S2 TOTAL EFFORT (HOURS) | [5 empty] | 113
SPRINT 3 BACKLOG
US-020 | 1 | Discussion with Team Members, Requirement Analysis & Project Planning | 2025-07-28 | 2025-07-28 | Frontend Team | Others | 3- Completed | 4 | Day 1: 4
US-021 | 2 | Developed Finance Officer Dashboard with features included like create fund disbursement, initi... | 2025-07-28 | 2025-07-30 | Archana | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-021 | 3 | Developed Finance Officer Dashboard with features included like create fund disbursement, initi... | 2025-07-28 | 2025-07-30 | Archana | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-022 | 4 | Updated File structure of frontend according to industrial approach | 2025-07-28 | 2025-07-29 | Akshay Menon | Coding | 3- Completed | 5 | Day 1: 4; Day 2: 1
US-023 | 5 | Integration of Frontend and Backend APIs of Modules 1.Auth Module , 2. Admin Module, 3. Officer... | 2025-07-28 | 2025-07-31 | Akshay Menon | Build | 3- Completed | 10 | Day 1: 4; Day 2: 3; Day 3: 2; Day 4: 1
US-023 | 6 | Integration of Frontend and Backend APIs of Modules 1.Auth Module , 2. Admin Module, 3. Officer... | 2025-07-31 | 2025-08-03 | Akshay Menon | Build | 3- Completed | 10 | Day 1: 4; Day 2: 3; Day 3: 2; Day 4: 1
US-024 | 7 | Worked on reamining M2 -- officer workflow | 2025-07-29 | 2025-07-29 | Arsath Maideen | Others | 3- Completed | 4 | Day 1: 4
US-025 | 8 | Started working on M3-modules | 2025-07-30 | 2025-07-30 | Arsath Maideen | Others | 2- In Progress | 4 | Day 1: 4
US-026 | 9 | Worked on Staged Disbursement & Milestone Scheduling | 2025-07-31 | 2025-08-01 | Jeevan Manoj | Others | 3- Completed | 5 | Day 1: 4; Day 2: 1
US-027 | 10 | Worked on Compliance Tracking & Reminder Automation | 2025-08-01 | 2025-08-02 | Jeevan Manoj | Others | 3- Completed | 5 | Day 1: 4; Day 2: 1
US-029 | 11 | Given Idea for the analytics dashboard for each officer as per their requirements based on exis... | 2025-08-03 | 2025-08-04 | Jeevan Manoj | Others | 2- In Progress | 7 | Day 1: 4; Day 2: 3
US-030 | 12 | Developed Analytics Dashboard for each officer UI which has data visualisation tools like pie c... | 2025-08-04 | 2025-08-06 | Akshay Menon | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-030 | 13 | Developed Analytics Dashboard for each officer UI which has data visualisation tools like pie c... | 2025-08-07 | 2025-08-09 | Akshay Menon | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-031 | 14 | Developed code for backend by sending required DTO's to frontend for data visualisation in Anal... | 2025-08-05 | 2025-08-07 | Akshay Menon | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-031 | 15 | Developed code for backend by sending required DTO's to frontend for data visualisation in Anal... | 2025-08-08 | 2025-08-10 | Akshay Menon | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
|  | S3 TOTAL EFFORT (HOURS) | [5 empty] | 108
SPRINT 4 BACKLOG
US-032 | 1 | Verification and testing for beneficiary login and signup and data saved in the Database | 2025-08-11 | 2025-08-12 | Arsath Maideen | System Test | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-033 | 2 | Testing done by handling various test cases provided by the mentor for application submission m... | 2025-08-11 | 2025-08-12 | Arsath Maideen | System Test | 3- Completed | 7 | Day 1: 4; Day 2: 3
US-034 | 3 | Testing for officer registration as well as approving request by admin leading to registration... | 2025-08-11 | 2025-08-13 | Arsath Maideen | System Test | 3- Completed | 8 | Day 1: 4; Day 2: 3; Day 3: 1
US-035 | 4 | Testing for Admin allocating the applications to 4 different officers done successfully. Along... | 2025-08-13 | 2025-08-14 | Arsath Maideen | System Test | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-035 | 5 | Testing for Admin allocating the applications to 4 different officers done successfully. Along... | 2025-08-15 | 2025-08-16 | Arsath Maideen | System Test | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-036 | 6 | Testing for Stage by Stage Disbursement funds to the beneficary done successfully | 2025-08-15 | 2025-08-16 | Arsath Maideen | System Test | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-037 | 7 | Modified the frontend UI of Admins Dashboard with better navigation to each pages, developed a... | 2025-08-17 | 2025-08-19 | Akshay Menon | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-037 | 8 | Modified the frontend UI of Admins Dashboard with better navigation to each pages, developed a... | 2025-08-20 | 2025-08-22 | Akshay Menon | Coding | 3- Completed | 9 | Day 1: 4; Day 2: 3; Day 3: 2
US-038 | 9 | Modified the backend APIs correcting the flow of the application documents and identified the b... | 2025-08-19 | 2025-08-20 | Akshay Menon | Design | 3- Completed | 7 | Day 1: 4; Day 2: 3
US-039 | 10 | Updated frontend Officer dashboard by adding the field inspection report to field officer which... | 2025-08-21 | 2025-08-22 | Akshay Menon | Design | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-039 | 11 | Updated frontend Officer dashboard by adding the field inspection report to field officer which... | 2025-08-23 | 2025-08-24 | Akshay Menon | Design | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-040 | 12 | Updated frontend as well as the backend of the beneficary module management eliminating the bug... | 2025-08-23 | 2025-08-24 | Akshay Menon | Coding | 3- Completed | 6 | Day 1: 4; Day 2: 2
US-041 | 13 | Integrated Security Based Roles, restricted APIs Roles based access,Authentication and authoriz... | 2025-08-25 | 2025-08-27 | Akshay Menon | Coding | 3- Completed | 8 | Day 1: 4; Day 2: 3; Day 3: 1
US-041 | 14 | Integrated Security Based Roles, restricted APIs Roles based access,Authentication and authoriz... | 2025-08-28 | 2025-08-30 | Akshay Menon | Coding | 3- Completed | 8 | Day 1: 4; Day 2: 3; Day 3: 1
|  | S4 TOTAL EFFORT (HOURS) | [5 empty] | 98
Note on D2: ====== ID#AAACAAPd2c0 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAACAAPd2c8 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAACAAPd2dg Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAACAAPd2dQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAACAAPd2cs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAACAAPd2dc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAACAAPd2dI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAACAAPd2cw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAACAAPd2dk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAACAAPd2dA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAACAAPd2dU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAACAAPd2ck Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAACAAPd2dM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAACAAPd2dE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAACAAPd2do Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAACAAPd2dY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAACAAPd2co Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | Unclear project requirements and workflow steps at kickoff | Held a team discussion on workflow and business logic before starting implementation; documented decisions
S1 | Day 10 | OCR research task (US-008) lacked a clear time-box, risking scope creep | Time-boxed further OCR exploration and carried the task forward to the next milestone as incomplete
S2 | Day 5 | Dependency fields left blank for tasks that relied on earlier auth/API work | Reviewed and corrected dependency tracking; aligned module owners before starting new APIs
S2 | Day 12 | Large modules (dashboards, core APIs) needed parallel work across multiple people | Split community/officer/admin dashboards and backend APIs across team members to work in parallel
S3 | Day 4 | Leftover M2 work (officer workflow, US-024) needed explicit tracking into the new sprint | Logged the carried-over item explicitly instead of folding it silently into M3 scope
S3 | Day 11 | Some integration tasks were assigned to a generic 'Frontend Team' instead of a named owner | Reassigned frontend-backend integration tasks to named individuals for accountability
S4 | Day 3 | Bug fixes had previously been merged without re-verifying the full end-to-end flow | Adopted role-by-role testing (beneficiary, officer, admin, finance officer) before integration testing
S4 | Day 9 | Test cases were written only after development, delaying bug discovery | Started writing test cases alongside development for each module going forward

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-06-30 | 2025-07-13 | Arsath Maideen, Akshay Menon, Archana, Jeevan Manoj, Praveena | Documenting workflow and API design decisions before starting implementation | Starting research tasks (e.g. OCR) without a clear time-box, causing US-008 to remain incomplete | Discussing project workflow and business logic as a team before assigning tasks | Set up Git repo, ER diagram, workflow diagrams and API design docs; OCR research task carried forward as incomplete to next milestone
2 | S2 | 2025-07-14 | 2025-07-27 | Arsath Maideen, Akshay Menon, Archana, Jeevan Manoj, Praveena, Sahanaa | Splitting large modules (dashboards, APIs) across multiple people to work in parallel | Leaving dependency fields blank for tasks that clearly relied on earlier auth/API work | Completing full modules end-to-end (UI + backend API) within the same milestone | Delivered login, community/officer/admin dashboards, JWT authentication, and core APIs for beneficiary, scheme and application modules
3 | S3 | 2025-07-28 | 2025-08-10 | Arsath Maideen, Akshay Menon, Archana, Jeevan Manoj | Tracking partially finished work explicitly (e.g. leftover M2 items) instead of folding it silently into the new milestone | Assigning tasks to a generic 'Frontend Team' instead of a named individual | Integrating frontend and backend modules together rather than finishing them in isolation | Delivered Finance Officer dashboard, module integration, staged disbursement and analytics dashboard; officer workflow (US-025) and analytics dashboard idea (US-029) carried into next milestone as in-progress
4 | S4 | 2025-08-11 | 2025-08-30 | Arsath Maideen, Akshay Menon | Writing test cases before/alongside development for each module rather than only at the end | Merging bug fixes without re-verifying the full flow (login to disbursement) end-to-end | Testing each role's flow (beneficiary, officer, admin, finance officer) individually before integration testing | Completed verification/testing for login, signup, application submission, officer approval, stage-based disbursement, and role-based access control; fixed identified bugs in application flow